## Sheet1
TIMELINE DETAILS |  |  |  | YEAR | 2021 | [25 empty] | 2022
|  |  |  | QUARTER | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [15 empty] | Q2 | [15 empty] | Q3 | [15 empty] | Q4
|  |  |  | MONTH | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY | [5 empty] | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY | [5 empty] | JUNE |  |  |  |  | JULY | [5 empty] | AUGUST |  |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER | [5 empty] | NOVEMBER |  |  |  |  | DECEMBER
PLANT | SERVER NAME | DATABASE NAME | STATUS | WEEK LINE | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 14 | 15 | 16 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | 23 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 31 | 32 | 32 | 33 | 34 | 35 | 36 | 36 | 37 | 38 | 39 | 40 | 40 | 41 | 42 | 43 | 44 | 45 | 45 | 46 | 47 | 48 | 49 | 49 | 50 | 51 | 52 | 53
CJA 1 | SP74W0026 | fa_sfds8 | Complete Deployment | LAVA 8 | bar: JULY 28 to AUGUST 35
CJA 1 | SP74W0027 | fa_sfds24 | Complete Deployment | LAVA 24 | bar: AUGUST 34 to NOVEMBER 48
CJA 2/3 | SP74W0015 | fa_sfds25 | On-going Deployment (80%) | LAVA 25 | bar: NOVEMBER 47 to JANUARY 4
CJA 2/3 | SP74W0014 | fa_sfds26 | On-going Deployment (80%) | LAVA 26 | bar: JANUARY 3 to APRIL 15
CJA 2/3 | S74W0087 | fa_sfds22 | On-going Deployment | LAVA 22 | bar: APRIL 15 to JUNE 27
CJA 2/3 | S74W0009 | fa_sfds1 | Not Started | MAGMA 1 | bar: MAY 22 to AUGUST 34
CJA 2/3 | S74W0051 | fa_sfds4 | Not Started | MAGMA 4 | bar: JULY 32 to SEPTEMBER 40
TBC | N/A | N/A | No Database Access (May need to look for alternative access database or HP Support is needed) | MAGMA 3 | bar: JUNE 23 to DECEMBER 51
TBC | N/A | N/A | No Database Access (May need to look for alternative access database or HP Support is needed) | LAVA 19 | bar: JUNE 23 to DECEMBER 51
TBC | N/A | N/A | No Database Access (May need to look for alternative access database or HP Support is needed) | LAVA 20 | bar: JUNE 23 to DECEMBER 51

## Sheet2
Line | Dashboard Arcstone | Production Report | Remarks
LAVA 8 | Complete | Complete
LAVA 24 | Complete | Complete
LAVA 25 | Complete | On-going | Need System Member Upgrade Data Collect PC at CJA2
LAVA 26 | Complete | On-going | Need System Member Upgrade Data Collect PC at CJA3
LAVA 22 | Halt Progress | Halt Progress | Need to find L22 Current Server
MAGMA 1 | On-going | On-going
MAGMA 4 | On-going | On-going
LAVA 19 | HP SUPPORT REQUIRED | HP SUPPORT REQUIRED | Database Server Access Error
LAVA 20 | HP SUPPORT REQUIRED | HP SUPPORT REQUIRED | Database Server Access Error
MAGMA 3 | HP SUPPORT REQUIRED | HP SUPPORT REQUIRED | Database Server Access Error

## Sheet3
YEAR | 2021 | [25 empty] | 2022
QUARTER | Q3 | [12 empty] | Q4 | [12 empty] | Q1 | [15 empty] | Q2 | [15 empty] | Q3 | [15 empty] | Q4
MONTH | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY | [5 empty] | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY | [5 empty] | JUNE |  |  |  |  | JULY | [5 empty] | AUGUST |  |  |  |  | SEPTEMBER |  |  |  |  | OCTOBER | [5 empty] | NOVEMBER |  |  |  |  | DECEMBER
WEEK LINE | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 13 | 14 | 14 | 15 | 16 | 17 | 18 | 18 | 19 | 20 | 21 | 22 | 23 | 23 | 24 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 31 | 32 | 32 | 33 | 34 | 35 | 36 | 36 | 37 | 38 | 39 | 40 | 40 | 41 | 42 | 43 | 44 | 45 | 45 | 46 | 47 | 48 | 49 | 49 | 50 | 51 | 52 | 53
LAVA 8
LAVA 24
LAVA 25
LAVA 26
LAVA 22
MAGMA 1
MAGMA 4
MAGMA 3
LAVA 19
LAVA 20